## Sheet1
ID | Task | Description | Tag | Minimal Duration (Hrs) | Maximum Duration (Hrs) | Difference (Hrs)
0 | DI | Research effective test conditions for entire simulation, i.e. locations, conditions, controlled variables etc. | P1 | 3 | 7.5 | 4.5
1 | DI | Define ideal test conditions for entire simulation, i.e. locations, conditions, controlled variables etc. | P1 | 1.5 | 3 | 1.5
2 | SA | Define solar array model input and output variables. | P1 | 2 | 5 | 3
3 | SA | Investigate solar array model behaviours, taking inputs defined and turning them into outputs defined. | P1 | 7.5 | 15 | 7.5
4 | SA | Gather data of solar array behaviour for a changing angle of incidence, experimentally | P1 | 4 | 7.5 | 3.5
5 |  | Process experimental data |  | 2 | 4 | 2
6 | SA | Compile solar array research | P1 | 3 | 5 | 2
8 | SA | Derive test cases for solar array model | P1 | 3 | 5 | 2
9 | MO | Define motor model input and output variables. | P1 | 0.5 | 2 | 1.5
10 | MO | Investigate motor models and behaviours, taking inputs defined and turning them into outputs defined. | P1 | 7.5 | 15 | 7.5
11 | MO | Derive dataset to validate motor model acquired or developed | P1 | 2 | 4 | 2
12 | MO | Compile motor model research | P1 | 3 | 5 | 2
13 | MO | Derive test cases for motor model | P1 | 2 | 4 | 2
14 | LO | Record research points in logbook | P1 | 5 | 7.5 | 2.5
15 | SI | Define solar irradiance model input and output variables. | P1 | 2 | 5 | 3
16 | SI | Investigate solar irradiance model and behaviours, taking inputs defined and turning them into outputs defined. | P1 | 11.25 | 15 | 3.75
17 | SI | Derive dataset to validate solar irradiance model acquired or developed | P1 | 7.5 | 15 | 7.5
18 | SI | Compile irradiance model research | P1 | 3 | 5 | 2
19 | SI | Derive test cases for irradiance model | P1 | 2 | 4 | 2
79 | CA | Define control algorithm input and output variables. | P1 | 2 | 5 | 3
20 | CA | Investigate control algorithm model and behaviours, taking identified inputs and turning them to desired outputs. | P1 | 11.25 | 15 | 3.75
21 | CA | Derive dataset to validate control algorithm model acquired or developed | P1 | 7.5 | 15 | 7.5
22 | CA | Compile control algorithm model research | P1 | 3.75 | 7.5 | 3.75
23 | CA | Derive test cases for control algorithm model | P1 | 3.75 | 7.5 | 3.75
24 | DI | Define crucial results which need to be gathered by the sumulation to analyse approaches effectively. | P1 | 2 | 3.75 | 1.75
25 | DI | Define a hypothesis, and thus a null hypothesis by which the significance of the study can be measured about. | P1 | 1 | 2 | 1
26 | LO | Record research points in logbook | P1 | 3.75 | 5 | 1.25
27 | RE | Review of research points | P1 | 3.75 | 7.5 | 3.75
28 | CO | Compile all key research into dissertation document. | P1 | 7.5 | 11.25 | 3.75
29 | SU | Discuss research with my supervisor, reviewing methodologies. | P1 | 2 | 2.5 | 0.5
30 | SI | Develop solar irradiance algorithm to link the inputs and outputs | P2 | 7.5 | 15 | 7.5
31 | SI | Test identified model using developed test cases. | P2 | 2 | 5 | 3
32 |  | Investigate test failures, correcting and rerunning tests | P2 | 0 | 7.5 | 7.5
33 | SI | Validate model using data gathered | P2 | 1 | 3.75 | 2.75
34 |  | Investigate validation failures | P2 | 0 | 7.5 | 7.5
35 | LO | Compile project progress in logbook | P2 | 2 | 4 | 2
36 | CO | Compile progress into dissertation | P2 | 5 | 7.5 | 2.5
37 | RE | Review project progress | P2 | 1 | 2 | 1
38 | SA | Develop solar array model | P2 | 3.75 | 7.5 | 3.75
39 | SA | Test identified model using developed test cases. | P2 | 3.75 | 7.5 | 3.75
40 |  | Investigate test failures, correcting and rerunning tests | P2 | 0 | 3.75 | 3.75
41 | SA | Validate model using data gathered | P2 | 2 | 5 | 3
42 |  | Investigate validation failures | P2 | 0 | 3.75 | 3.75
43 | LO | Compile project progress in logbook | P2 | 2 | 4 | 2
44 | CO | Compile progress into dissertation | P2 | 3.75 | 7.5 | 3.75
45 | RE | Review project progress | P2 | 2 | 3 | 1
46 | CA | Develop control algorithm linking identified inputs to desired outputs | P2 | 15 | 22.5 | 7.5
47 | CA | Test identified model using developed test cases. | P2 | 7.5 | 11.25 | 3.75
48 |  | Investigate test failures, correcting and rerunning tests | P2 | 0 | 7.5 | 7.5
49 | CA | Validate model using data gathered | P2 | 3.75 | 5 | 1.25
50 |  | Investigate validation failures | P2 | 0 | 7.5 | 7.5
51 | LO | Compile project progress in logbook | P2 | 4 | 6 | 2
52 | CO | Compile progress into dissertation | P2 | 7.5 | 15 | 7.5
53 | RE | Review project progress | P2 | 3 | 5 | 2
54 | MO | Develop motor model linking identified inputs to desired outputs | P2 | 3.75 | 7.5 | 3.75
55 | MO | Test identified model using developed test cases. | P2 | 3.75 | 5 | 1.25
56 |  | Investigate test failures, correcting and rerunning tests | P2 | 0 | 7.5 | 7.5
57 | MO | Validate model using data gathered | P2 | 2 | 4 | 2
58 |  | Investigate validation failures | P2 | 0 | 7.5 | 7.5
59 | LO | Compile project progress in logbook | P2 | 2 | 4 | 2
60 | CO | Compile progress into dissertation | P2 | 3.75 | 5 | 1.25
61 | RE | Review project progress | P2 | 2 | 4 | 2
62 | RE | Major review of process | P2 | 3.75 | 7.5 | 3.75
63 | SU | Discuss developments with my supervisor. | P2 | 2 | 3 | 1
64 | RE | Regression test run | P3 | 7.5 | 15 | 7.5
65 | RE | Troubleshooting regression run | P3 | 0 | 15 | 15
66 | LO | Compile regression test results in logbook | P3 | 2 | 4 | 2
67 | CO | Compile regression test results and methodologies in dissertation document | P3 | 3.75 | 5 | 1.25
68 | RU | Run simulation based on test cases defined for entire system, gathering data defined. | P3 | 7.5 | 15 | 7.5
69 | RU | Troubleshoot data issues | P3 | 0 | 15 | 15
70 | AN | Compile data into appropriate graphs | P3 | 2 | 4 | 2
71 | AN | Analyse data against test cases and outcomes | P3 | 3.75 | 5 | 1.25
72 | AN | Analyse data against hypothesis, statistically | P3 | 3.75 | 5 | 1.25
73 | SU | Discuss data gathered with supervisor | P3 | 2 | 3 | 1
74 | DI | Discuss each method using graphs and figures to support argments. | P3 | 15 | 22.5 | 7.5
75 | DI | Write a final conclusion, discussing the study and its results and defining its success suscinctly. | P3 | 2 | 4 | 2
76 | RE | Review compiled report | P3 | 7.5 | 15 | 7.5
77 | SU | Discuss dissertation with supervisor and peers | P3 | 0 | 0 | 0
78 | FIN | Submit dissertation | P3 | 0 | 0 | 0
|  |  |  | 276.25 | 572 | 295.75
|  |  |  | 36.8333 | 76.2667 | 39.4333